## UOJ DevSecOps Checklist
ADCB DevSecOps Security Baseline — UOJ Compliance Tracker
Unified Onboarding Journey (UOJ) · F.1 CI/CD Pipeline Controls · 41 items ¦ Update 'UOJ Status' column as work progresses
ID | Category | Control Summary | UOJ Status | Owner | Target Date | Evidence / Notes | Priority | Blocker? | Linked JIRA
1.1 | Pipeline Infra | All build and deployment jobs run on ephemeral, short-lived agents provisioned dynamically and destroyed immediately after completion. | Not Started |  |  |  | High | No
1.2 | Access & IAM | All source code repositories remain private; access restricted to corporate network or trusted VPN endpoints. | Not Started |  |  |  | High | No
1.3 | Pipeline Infra | Builds execute in isolated, ephemeral environments. No shared resources, credentials, or network access across concurrent jobs. Least-privilege agents. | Not Started |  |  |  | High | No
1.4 | Branch & Code | Pipeline/workflow files reside in version control and changed only through approved pull requests. | Not Started |  |  |  | High | No
1.5 | Access & IAM | Build agents authenticate to cloud providers using least-privilege IAM roles or service principals scoped to their function. | Not Started |  |  |  | High | No
1.6 | Pipeline Infra | Self-hosted runners use a minimalistic, CIS-hardened OS image with only essential components. Regularly patched and re-baselined. | Not Started |  |  |  | High | No
1.7 | Pipeline Infra | Self-hosted runners operate in isolated subnets/VNets with private endpoints and restricted egress. | Not Started |  |  |  | High | No
1.8 | Secrets Mgmt | Runners must not persist secrets. Injected at runtime via OIDC/short-lived credentials. Never written to disk, cached, or stored in images. | Not Started |  |  |  | Critical | No
1.9 | Pipeline Infra | All self-hosted runners centrally registered, integrity-checked, and monitored. Unverified runners blocked. | Not Started |  |  |  | High | No
1.10 | Pipeline Infra | Runners use authenticated/trusted channels, minimal secret/token scope, and operate as single-use ephemeral instances destroyed on job completion. | Not Started |  |  |  | High | No
1.11 | Pipeline Infra | Pipelines follow single-responsibility principle. Build/test/deploy stages use separate identities/environments. No shared credentials across prod/non-prod. | Not Started |  |  |  | High | No
1.12 | Branch & Code | Protected branches (main/master/release/*) enforce mandatory approval workflows, segregation of duties, security scans, and policy gates before merge. | Not Started |  |  |  | Critical | No
1.13 | Branch & Code | All commits must be cryptographically signed using GPG or X.509 certs linked to verified corporate identities. | Not Started |  |  |  | High | No
1.14 | Branch & Code | All releases tagged, signed, and immutable. Unique cryptographic tag per release. Tags protected from modification/deletion. | Not Started |  |  |  | High | No
1.15 | Access & IAM | Identities operate under least privilege. Admin/write/merge privileges restricted to designated maintainers. Access changes audited and periodically reviewed. | Not Started |  |  |  | High | No
1.16 | Access & IAM | Access to VCS federated through Entra ID SSO with Conditional Access enforcing MFA. Service accounts use short-lived OIDC tokens, not static credentials. | Not Started |  |  |  | Critical | No
1.17 | Branch & Code | AI-assisted coding uses enterprise-managed instances with DLP controls. AI-generated code scanned before merge. | Not Started |  |  |  | Medium | No
1.18 | Branch & Code | Branch protection rules must not be bypassable. Enforcement settings immutable. Break-glass procedure required for emergency overrides. | Not Started |  |  |  | Critical | No
1.19 | Branch & Code | Main branch fully protected: mandatory approvals, signed commits, passing status checks. Direct commits strictly prohibited except via approved CI/CD automation. | Not Started |  |  |  | Critical | No
1.20 | Dependency & SCA | Controlled dependency acquisition: packages fetched only through approved internal mirrors/registries. Direct public Internet downloads blocked. | Not Started |  |  |  | High | No
1.21 | Dependency & SCA | Vetting process for all third-party resources (packages, containers, templates) before approval for local use. | Not Started |  |  |  | High | No
1.22 | Dependency & SCA | All project dependencies explicitly pinned to fixed, verified versions. Floating/wildcard/latest specifiers prohibited in production CI/CD builds. | Not Started |  |  |  | High | No
1.23 | Dependency & SCA | Projects include validated lock files (package-lock.json, Pipfile.lock etc.). Any dependency update triggers automated SCA review. | Not Started |  |  |  | High | No
1.24 | SAST / DAST | All CI/CD pipelines integrate automated SCA. Scans run on every build and pull request. Critical/high-severity findings block promotion or merge. | Not Started |  |  |  | Critical | No
1.25 | Dependency & SCA | All dependencies sourced exclusively from trusted/approved registries. Signature verification, TLS encryption, and access control enforced. | Not Started |  |  |  | High | No
1.26 | Secrets Mgmt | Automated secrets scanning at every SDLC stage including pre-commit, pull request, and build. Detected secrets trigger immediate alert and automated revocation. | Not Started |  |  |  | Critical | No
1.27 | SAST / DAST | All application source code undergoes automated SAST using enterprise-approved solution. Incremental scans on every PR to main/release. Critical/high findings block merge. | Not Started |  |  |  | Critical | No
1.28 | SAST / DAST | All applications undergo automated DAST within CI/CD and pre-production. Includes web + API runtime scanning. Critical/high findings block promotion. | Not Started |  |  |  | Critical | No
1.29 | IaC Security | All IaC templates scanned for misconfigurations before deployment. Aligned with CIS Benchmarks, NIST 800-53. Critical findings block deployment. | Not Started |  |  |  | Critical | No
1.30 | Env Segregation | All DevSecOps environments logically segregated (Dev/Test/Staging/Prod). Separate identities, pipelines, data, and secrets per environment. No cross-env credential sharing. | Not Started |  |  |  | Critical | No
1.31 | Env Segregation | All promotions between environments governed by automated promotion gates verifying artifact integrity, scan results, approval workflows, and policy compliance. | Not Started |  |  |  | High | No
1.32 | Secrets Mgmt | All secrets stored exclusively in approved enterprise secrets management systems (Azure Key Vault, AWS Secrets Manager, HashiCorp Vault). Must never reside in code/images/CI configs. | Not Started |  |  |  | Critical | No
1.33 | Container & Artifacts | Container images immutable, reproducible, and verifiably trusted. Referenced by digest (SHA256). Each build generates cryptographically signed SBOM and provenance attestation. | Not Started |  |  |  | High | No
1.34 | Container & Artifacts | Container images undergo automated vulnerability scanning during build, pre-deployment, and at runtime. Critical/high findings block image promotion. | Not Started |  |  |  | Critical | No
1.35 | Container & Artifacts | All build artifacts cryptographically signed at build time. Deployment pipelines verify signatures and provenance attestations. Unsigned artifacts blocked. | Not Started |  |  |  | High | No
1.36 | Container & Artifacts | Build pipelines generate SBOM for every compiled or containerized artifact. SBOMs stored securely in centralized evidence repository for compliance retention. | Not Started |  |  |  | High | No
1.37 | Container & Artifacts | Build artifacts stored in immutable, encrypted repositories with cryptographic signature verification. Encryption at rest and in transit enforced. | Not Started |  |  |  | High | No
1.38 | Policy as Code | All DevSecOps environments implement Policy-as-Code (PaC) to enforce security, compliance, and operational guardrails. Policies version-controlled and auditable. | Not Started |  |  |  | High | No
1.39 | Monitoring & Audit | CI/CD pipelines continuously monitored for unauthorized changes, anomalous executions, and deviations. Real-time visibility into pipeline activity and credential usage. | Not Started |  |  |  | High | No
1.40 | Monitoring & Audit | All CI/CD pipeline logs immutably stored and forwarded to centralized SIEM. Logs protected from modification/deletion, digitally signed, and retained per policy. | Not Started |  |  |  | High | No
1.41 | Monitoring & Audit | All developer workstations and cloud-based DevBoxes operate in isolated, secured, managed environments. All dev activity logged and monitored. | Not Started |  |  |  | Medium | No

## Dashboard
UOJ DevSecOps — Compliance Dashboard
Auto-calculated from Checklist sheet · Last updated: see date column
Total Controls | 41 | Category | Total | Compliant | In Progress | Not Started
Compliant | 0 | Pipeline Infra | 7 | 0 | 0 | 7
In Progress | 0 | Access & IAM | 4 | 0 | 0 | 4
Not Started | 41 | Secrets Mgmt | 3 | 0 | 0 | 3
N/A | 0 | Branch & Code | 7 | 0 | 0 | 7
% Complete | 0% | Dependency & SCA | 5 | 0 | 0 | 5
Critical Controls | 13 | SAST / DAST | 3 | 0 | 0 | 3
Critical Compliant | 0 | IaC Security | 1 | 0 | 0 | 1
Blockers Active | 0 | Container & Artifacts | 5 | 0 | 0 | 5
|  | Env Segregation | 2 | 0 | 0 | 2
|  | Monitoring & Audit | 3 | 0 | 0 | 3
|  | Policy as Code | 1 | 0 | 0 | 1

## Legend
Legend & Instructions
Type | Value | Meaning
Status | Compliant | Control fully implemented and verified with evidence
Status | In Progress | Control partially implemented or under active work
Status | Not Started | Control not yet started
Status | N/A | Control not applicable to UOJ scope
Priority | Critical | Must be addressed before production go-live
Priority | High | Should be addressed in current sprint
Priority | Medium | Address in next 2 sprints
Priority | Low | Nice to have / future hardening